## Document metadata

name: MOTD Sprint Tasking

overview: Break down all remaining MOTD MVP work into small ClickUp-ready tasks. Lead owns MongoDB models + seed data; Dev A/B/C each own backend + frontend for their modules. Ready-made is admin-only size returns (low priority). Tailors self-register, admin approves, then tailors manage shop + designs. Custom tailoring customer flow is primary. Shared auth/API client runs first on Dev A.

# MOTD MVP — Sprint Task Breakdown (ClickUp Ready)

## Current state (done)

| Area | Status |
| --- | --- |
| Repo structure (`frontend/`, `backend/`) | Done |
| Next.js 14 + next-intl + Tailwind | Done |
| Express auth (JWT signup/signin/profile) | Done — [`backend/routes/userRoutes.js`](backend/routes/userRoutes.js) |
| Homepage UI (all 13 sections, mock data) | Done — [`frontend/src/app/[locale]/page.tsx`](frontend/src/app/[locale]/page.tsx) |
| Design assets, tokens, i18n messages | Done |
| Domain models, business APIs, seed | Not started |
| Customer flows (cart, checkout, configurator) | Not started |
| Admin panel | Not started |
| Frontend auth + API integration | Not started |

## Ready-made items — listing idea

Keep all naming: ReadyMadeProduct, ready-made routes, ready-made UI labels. Only the business logic behind listings changes:

| Rule | Detail |
| --- | --- |
| Naming | Still called ready-made item everywhere (model, API, pages, admin) |
| Who lists | MOTD platform owner (admin) only — no seller/partner listings |
| What gets listed | A returned garment from a previous custom tailoring order (size issue only in MVP) |
| Stock | Typically 1 unit per item (the exact returned piece) |
| Priority | Low — custom tailoring is the main flow; build ready-made after auth |
| Homepage section | Keep design placement + "ready-made" naming; optional subtitle can mention size availability |

Removed from scope: seller attribution, seller role, partner-created listings, large general catalog.

Admin workflow: Custom order returned for size → admin creates a ready-made item linked to that order (sourceCustomOrderId, size, condition, price).

## Tailor accounts — self-register + admin approval

Tailors manage their own shop and designs after MOTD admin approval:

[Flowchart diagram — see digital plan for visual]

| Rule | Detail |
| --- | --- |
| Registration | Tailor creates own account (role `tailor`) via tailor signup flow |
| Before approval | Can log in but sees pending approval screen — cannot publish shop or designs publicly |
| After approval | Tailor creates/edits one shop (name, profile, logo) and CRUD own designs (basePrice, tailoringFee, etc.) |
| Admin role | Approve or reject tailor accounts — not create tailor shops/designs on their behalf |
| Public catalog | Customer-facing tailor/design APIs only return shops whose owner is `approved` + `isActive` |
| Fabrics | Unchanged — `fabric_store` partners still admin-managed in MVP (unless specified later) |

User model addition (Lead): approvalStatus: pending | approved | rejected — required for tailor role; default approved for customer, admin, fabric_store.

## Team assignment model

[Flowchart diagram — see digital plan for visual]

| Person | Owns (balanced mix) |
| --- | --- |
| Lead | All Mongoose schemas, seed script, sample data, schema handoff doc |
| Dev A | API client + token + login + navbar · ready-made module · homepage/fabric/tailor customer pages |
| Dev B | Auth context · custom order backend + configurator · tailor signup/backend + tailor dashboard |
| Dev C | Customer signup · full admin panel · tailor shop/designs UI · deploy support |

Rule: Each dev builds both backend routes and frontend pages for their module. Lead unblocks everyone with models + seed only.

## Dependency order — can devs work in parallel?

mix tasks from day one after Lead finishes models (L-01–L-08). You do not need all of S1 done before S2. Only 2 small shared gates block frontend integration:

| Gate | Task | Owner | Blocks | Est. |
| --- | --- | --- | --- | --- |
| Gate 1 | A-01 API client | Dev A (Day 1 AM) | All frontend API calls | ~3h |
| Gate 2 | A-03 Auth context | Dev B (Day 1 PM) | Checkout, admin guard, tailor portal login | ~3h |

Everything else can run in parallel across Dev A / B / C once Lead merges models.

### What each dev can start independently (after models)

| Dev | Start immediately (no auth UI needed) | Needs Gate 1 (A-01) | Needs Gate 2 (A-03) |
| --- | --- | --- | --- |
| Dev A | A-07–A-11 ready-made backend | A-04 login, A-12+ frontend, B-11/B-12 homepage wiring | A-18 checkout |
| Dev B | B-01–B-10 custom backend, B-25–B-28 tailor backend | B-11–B-16 catalog pages, B-17+ configurator UI | B-23 checkout, B-30 tailor dashboard |
| Dev C | C-01–C-10 admin backend | C-11+ admin frontend pages | C-11 admin route guard |

Backend-first strategy (recommended): While Dev A builds A-01 (3h), Dev B and Dev C start their backend APIs (B-01, C-01) using Postman against local MongoDB. No idle time.

Seed timing: Devs can start backend before seed finishes (L-09). Frontend integration testing needs seed (L-14) for real slugs/data.

## Balanced team assignment (mix tasks from get-go)

Original assignee tags in task blocks below are module defaults. Use this table for equal load (~24–25 tasks each):

| Dev | Task count | Owns |
| --- | --- | --- |
| Dev A | 24 | A-01, A-02, A-04, A-06 (shared auth UI) · A-07–A-20 (ready-made) · B-11–B-16 (homepage + fabric/tailor customer pages) |
| Dev B | 25 | A-03 (auth context — do Day 1) · B-01–B-10 (custom backend) · B-17–B-24 (configurator) · B-25–B-30 (tailor signup API + registration + dashboard) |
| Dev C | 25 | A-05 (customer signup) · C-01–C-22 (all admin) · B-31–B-32 (tailor shop + designs UI) |

Polish tasks (P-01–P-10): Split evenly in final week — ~3–4 each, or assign P-08/P-09 deploy to Lead + Dev C.

### Suggested Week 1 schedule (equal burden)

| Day | Dev A | Dev B | Dev C |
| --- | --- | --- | --- |
| 1 | A-01, A-02 (API client + token) | A-03 (auth context) + B-01 pricing service | A-05 signup + C-01 admin middleware |
| 2 | A-07–A-09 ready-made APIs | B-02–B-06 fabric/tailor public APIs | C-02–C-05 admin CRUD APIs |
| 3 | A-04, A-06 login + navbar | B-07–B-10 custom order APIs | C-06–C-10 orders + settings APIs |
| 4 | A-10–A-11 + A-12 carousel | B-17 custom order context | C-11 admin layout |
| 5 | B-13–B-14 fabric pages | B-18–B-19 configurator steps | C-16 pending tailors page |

Week 2+: each dev continues their remaining tasks in parallel. Ready-made checkout (A-18–A-20) can slip — lowest priority.

### Rules for mixing

Lead tasks (L-01–L-14) — Lead only; blocks everyone until L-08 models done.

Do not duplicate A-01 or A-03 — one owner each; rest of auth UI is split (A-02/A-04/A-06 → Dev A, A-05 → Dev C, A-03 → Dev B).

Communicate on shared files — orders/page.tsx touched by Dev A (ready-made tab) and Dev B (custom tab); agree who creates shell first.

Postman collections — each dev documents their APIs as they ship; no need to wait for one "API complete" milestone.

## Original sprint labels (reference only)

| Sprint | Who | Gate |
| --- | --- | --- |
| S0 | Lead | Models L-01–L-08 → seed L-09–L-14 |
| S1 | Dev A + Dev B | Gates A-01 + A-03 only (~1 day), not all of A-01–A-06 |
| S2 | All 3 devs | Full parallel — backend + frontend per balanced table |
| S3 | All | Polish P-01–P-10 |
| S4 | Lead + Dev C | Deploy P-08–P-09, E2E P-10 |

## Task format (for ClickUp)

Copy each task as: Title = task name line · Description = Description field · Acceptance = Done when bullets.

| Field | Use |
| --- | --- |
| Assignee | Lead / Dev A / Dev B / Dev C |
| Type | Backend / Frontend / Full-stack |
| Est. | Rough hours |
| Blocked by | Prior task IDs |

## LEAD tasks (15 tasks) — do first

### Models (9 tasks)

L-01 · PlatformSettings model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Description | Create the MongoDB schema for platform-wide defaults (delivery fee, tailoring fee, VAT, currency). Single document used by pricing and admin settings. |
| Done when | [`backend/models/PlatformSettings.js`](backend/models/PlatformSettings.js) exists; singleton pattern; fields `defaultDeliveryFee`, `defaultTailoringFee`, `vatRate` (0.05), `currency: 'AED'`. |

L-01b · Extend User model — tailor approval

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | — |
| Description | Add approval workflow fields to User so tailor accounts can be pending until MOTD admin approves them. |
| Done when | [`backend/models/User.js`](backend/models/User.js) has `approvalStatus`: `pending` \ |

L-02 · ReadyMadeProduct model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Description | Define schema for ready-made items — admin-listed size returns from custom orders, not a general product catalog. |
| Done when | Model has bilingual fields, `returnReason`, `sourceCustomOrderId`, `condition`, `countInStock` default 1; no seller/`listedBy` ref. |

L-03 · Fabric model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Description | Define fabric catalog schema for the custom tailoring flow, including store attribution and pickup address. |
| Done when | Model has `pricePerMeter`, `material`, `listedByStore`, `storePickupAddress`, bilingual names, `isActive`. |

L-04 · TailorShop model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Description | Define tailor shop profile schema — one shop per approved tailor owner. |
| Done when | Model has profile fields, `ownerId` unique ref, `isActive`; public visibility gated by owner `approvalStatus: approved`. |

L-05 · Design model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Description | Define design schema linked to a tailor shop, with pricing fields used by the composite pricing engine. |
| Done when | Model has `tailorShopId` ref, `basePrice`, `tailoringFee`, `estimatedMeters`, bilingual fields; index on `tailorShopId`. |

L-06 · RetailOrder model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Description | Define order schema for ready-made purchases (retail/COD flow). Port pattern from archive order model. |
| Done when | Model has `orderType: 'retail'`, `orderItems[]`, shipping, payment, status enum, `userId`. |

L-07 · CustomOrder model

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Description | Define full custom tailoring order schema including fabric/design snapshots, measurements, logistics status pipeline, and pricing snapshot. |
| Done when | Model has `fabricSource`, snapshots, `measurements`, `pickupAddress`, 8-step `status` + `statusHistory[]`, `pricing` object, COD fields. |

L-08 · Schema handoff doc

| Assignee | Lead |
| --- | --- |
| Type | Docs |
| Est. | ~2h |
| Blocked by | L-01 through L-07 |
| Description | Write a short schema reference so Dev A/B/C know field names, enums, and relationships before building APIs. |
| Done when | `docs/schema.md` or README section posted; covers all models + tailor approval rules. |

### Seed (6 tasks)

L-09 · Seed script scaffold

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-01 through L-07 |
| Description | Create a repeatable dev seed script so the team can reset and populate test data locally. |
| Done when | [`backend/scripts/seed.js`](backend/scripts/seed.js) + `npm run seed`; clears/reseeds DB using env config. |

L-10 · Seed users + platform settings

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-09 |
| Description | Seed admin, approved tailors, one pending tailor, fabric_store partners, and default platform settings. |
| Done when | Admin login works; 1–2 approved + 1 pending tailor; PlatformSettings document exists. |

L-11 · Seed ready-made items (2–3 samples)

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~1h |
| Blocked by | L-09, L-02 |
| Description | Add a small set of sample ready-made items (size returns) for Dev A to test against. |
| Done when | 2–3 items with bilingual names, slugs, images, `returnReason: size_issue`, `countInStock: 1`. |

L-12 · Seed fabrics

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-09, L-03 |
| Description | Seed fabric catalog data matching homepage mock materials and prices. |
| Done when | ~9 fabrics with store attribution and pickup addresses seeded. |

L-13 · Seed tailor shops + designs

| Assignee | Lead |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-09, L-10, L-04, L-05 |
| Description | Seed approved tailor shops and their designs; pending tailor must have no public shop. |
| Done when | Approved tailors have shops + 2–4 designs each; pending tailor has none visible. |

L-14 · Verify seed + share credentials

| Assignee | Lead |
| --- | --- |
| Type | Full-stack |
| Est. | ~1h |
| Blocked by | L-10 through L-13 |
| Description | Run full seed, verify counts, and share test logins and sample slugs with the team. |
| Done when | Seed runs without errors; team has admin + tailor credentials and sample API slugs. |

## DEV A tasks — Auth + ready-made module (20 tasks, low priority after A-06)

### Shared foundation (6 tasks — Dev A, Sprint S1)

A-01 · API client utility

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | L-07 (optional — can stub) |
| Description | Build a shared fetch wrapper so all frontend modules call the Express API consistently with error handling. |
| Done when | [`frontend/src/lib/api/client.ts`](frontend/src/lib/api/client.ts) uses `NEXT_PUBLIC_API_URL`; JSON helpers; throws/parses API errors. |

A-02 · Auth token storage

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~1h |
| Blocked by | A-01 |
| Description | Persist JWT locally so logged-in users stay authenticated across page reloads. |
| Done when | [`frontend/src/lib/auth/token.ts`](frontend/src/lib/auth/token.ts) has save/get/clear token helpers. |

A-03 · Auth context provider

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-01, A-02 |
| Description | Provide global auth state (user, login, logout) for the whole Next.js app. |
| Done when | [`frontend/src/context/AuthContext.tsx`](frontend/src/context/AuthContext.tsx) loads profile on mount; exposes user + auth actions. |

A-04 · Sign-in page

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-03 |
| Description | Customer login page wired to backend signin API with bilingual UI. |
| Done when | [`frontend/src/app/[locale]/login/page.tsx`](frontend/src/app/[locale]/login/page.tsx) posts to `POST /api/users/signin`; redirects after success; EN/AR strings. |

A-05 · Sign-up page

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-03 |
| Description | Customer registration page for new buyer accounts. |
| Done when | [`frontend/src/app/[locale]/signup/page.tsx`](frontend/src/app/[locale]/signup/page.tsx) posts to `POST /api/users/signup`; EN/AR strings. |

A-06 · Wire LocaleSwitcher + nav auth state

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | A-03 |
| Description | Connect navbar to auth state and locale switcher so nav reflects logged-in user. |
| Done when | LocaleSwitcher in Navbar; Login/Account toggle; cart link placeholder wired. |

### Backend — Ready-made (5 tasks)

A-07 · GET ready-made list API

| Assignee | Dev A |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | L-02, L-14 |
| Description | Public API to list active ready-made items for homepage carousel and browsing. |
| Done when | `GET /api/ready-made` returns active items; optional size filter + pagination; mounted in server.js. |

A-08 · GET ready-made detail API

| Assignee | Dev A |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | A-07 |
| Description | Public API for a single ready-made item detail page including return context. |
| Done when | `GET /api/ready-made/:slug` returns item + optional source order summary; no seller info. |

A-09 · POST retail order API

| Assignee | Dev A |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | L-06, A-08 |
| Description | Create a retail order when customer checks out with ready-made cart (COD). |
| Done when | `POST /api/orders/retail` requires auth; validates stock; creates RetailOrder; returns order ID. |

A-10 · GET my retail orders API

| Assignee | Dev A |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | A-09 |
| Description | Let logged-in customers see their ready-made purchase history. |
| Done when | `GET /api/orders/retail/mine` returns user's retail orders only. |

A-11 · GET retail order detail API

| Assignee | Dev A |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | A-09 |
| Description | Fetch single retail order detail for order history view. |
| Done when | `GET /api/orders/retail/:id` restricted to owner or admin. |

### Frontend — Ready-made (9 tasks)

A-12 · Wire homepage ProductCarousel to API

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-01, A-07 |
| Description | Replace mock data in homepage ready-made carousel with live API data. |
| Done when | ProductCarousel fetches from API; shows loading, error, and empty states. |

A-13 · ProductCard link to detail + size badge

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~1h |
| Blocked by | A-12 |
| Description | Make carousel cards clickable and show item size on each card. |
| Done when | ProductCard links to `/[locale]/ready-made/[slug]`; size visible on card. |

A-14 · Ready-made item detail page

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | A-08, A-15 |
| Description | Full detail page for a ready-made item with add-to-cart action. |
| Done when | Detail page shows images, price, size, condition, ReadyMadeItemInfo, single-unit stock. |

A-15 · ReadyMadeItemInfo component

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | — |
| Description | UI note explaining this ready-made item came from a size return on a custom order. |
| Done when | Component shows return context + optional original design name; replaces SellerBadge. |

A-16 · Cart context (ready-made only)

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-03 |
| Description | Client-side cart state for ready-made items only, separate from custom order flow. |
| Done when | CartContext add/remove/update qty; persists to localStorage. |

A-17 · Cart page

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-16 |
| Description | Shopping cart page showing ready-made line items and price subtotal with VAT. |
| Done when | Cart page at `/cart` with qty controls, subtotal + VAT, link to checkout. |

A-18 · Checkout page — shipping form

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | A-17, A-04 |
| Description | Checkout form for UAE shipping address and COD payment selection. |
| Done when | Checkout page with emirate, city, phone fields; auth guard; COD only. |

A-19 · Checkout — place order + confirmation

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-09, A-18 |
| Description | Submit retail order to API and show order confirmation; clear cart and mark item sold. |
| Done when | Posts to retail order API; success screen; cart cleared; stock decremented. |

A-20 · Orders page — ready-made tab

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-10, B-24 (shell may be shared) |
| Description | Order history page tab showing customer's ready-made purchases separately from custom orders. |
| Done when | Orders page shell has ready-made tab with status badges; Dev B adds custom tab later. |

Removed (out of scope): standalone /ready-made catalog page, SellerBadge, seller partner flows.

## DEV B tasks — Custom tailoring + tailor portal (32 tasks)

### Backend — Catalog + pricing (8 tasks)

B-01 · Pricing engine service

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | L-01, L-05, L-07 |
| Description | Core pricing calculator for custom orders — design + fabric + tailoring + delivery + 5% VAT. |
| Done when | [`backend/services/pricingService.js`](backend/services/pricingService.js) handles storefront and self-fabric (`fabricCost = 0`). |

B-02 · GET fabrics list API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-03, L-14 |
| Description | Public API listing active fabrics for homepage and fabric selection step. |
| Done when | `GET /api/fabrics` returns active fabrics; optional material filter. |

B-03 · GET fabric detail API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | B-02 |
| Description | Public API for single fabric detail including store attribution and pickup address. |
| Done when | `GET /api/fabrics/:slug` populates store info + pickup address. |

B-04 · GET tailor shops list API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-04, L-01b, L-14 |
| Description | Public API listing tailor shops — only shops whose owner account is admin-approved. |
| Done when | `GET /api/tailors` returns active shops with approved owners only. |

B-05 · GET tailor shop detail API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | B-04 |
| Description | Public API for tailor shop profile page. |
| Done when | `GET /api/tailors/:slug` returns shop; 404 if owner not approved. |

B-06 · GET designs by tailor API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | B-05, L-05 |
| Description | Public API listing designs for a tailor shop (used in shop detail and configurator). |
| Done when | `GET /api/tailors/:slug/designs` returns active designs for that shop. |

B-07 · POST custom order price preview API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | B-01 |
| Description | Calculate and return itemized price breakdown before customer confirms custom order. |
| Done when | `POST /api/orders/custom/preview` accepts fabric/design/meters; returns breakdown; no DB save. |

B-08 · POST create custom order API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | B-01, B-07, L-07 |
| Description | Place a custom tailoring order with frozen pricing snapshot and initial status history. |
| Done when | `POST /api/orders/custom` requires auth; snapshots prices; sets status + statusHistory entry. |

### Backend — Custom order read (2 tasks)

B-09 · GET my custom orders API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | B-08 |
| Description | Let customers list their custom tailoring orders. |
| Done when | `GET /api/orders/custom/mine` returns authenticated user's custom orders. |

B-10 · GET custom order detail API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | B-08 |
| Description | Fetch full custom order including status history for tracking timeline. |
| Done when | `GET /api/orders/custom/:id` includes statusHistory; owner or admin only. |

### Frontend — Catalog pages (6 tasks)

B-11 · Wire homepage FabricCarousel to API

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | A-01, B-02 |
| Description | Replace mock fabric data on homepage with live API feed. |
| Done when | FabricCarousel fetches from `/api/fabrics`; loading/error states. |

B-12 · Wire homepage TailorGrid to API

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | A-01, B-04 |
| Description | Replace mock tailor cards on homepage with approved tailor shops from API. |
| Done when | TailorGrid fetches from `/api/tailors`; loading/error states. |

B-13 · Fabric detail page

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-03, B-14 |
| Description | Fabric detail page with store attribution and CTA to start custom order with this fabric. |
| Done when | Page at `/fabrics/[slug]` shows attributes, price/m, StoreAttribution, "Select for custom order". |

B-14 · StoreAttribution component

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | — |
| Description | UI block showing which fabric store listed the fabric (attribution only, not a browseable store section). |
| Done when | StoreAttribution component shows store name/info on fabric detail. |

B-15 · Tailors listing page

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | B-04 |
| Description | Browse page for all approved tailor shops. |
| Done when | Page at `/tailors` lists approved shops with cards linking to shop detail. |

B-16 · Tailor shop detail + design gallery

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-05, B-06 |
| Description | Tailor shop profile with design gallery; each design links into custom order configurator. |
| Done when | Page at `/tailors/[slug]` shows shop info + design cards with configurator links. |

### Frontend — Configurator (8 tasks)

B-17 · Custom order context/state

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-01 |
| Description | Session state holding customer's in-progress custom order selections across configurator steps. |
| Done when | CustomOrderContext stores fabric, self-fabric flag, tailor, design, meters, measurements; persists session. |

B-18 · Configurator step 1 — fabric selection

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-17, B-02 |
| Description | First configurator step — pick a platform fabric or choose "use my own fabric". |
| Done when | Page at `/custom-order/fabric` supports both fabric sources. |

B-19 · Configurator step 2 — tailor + design

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-17, B-04, B-06 |
| Description | Second step — browse approved tailors and select a design from chosen shop. |
| Done when | Page at `/custom-order/tailor` lets customer pick tailor + design. |

B-20 · Configurator step 3 — fabric meters input

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | B-17, B-19 |
| Description | Input for fabric meters needed; pre-fill suggested amount from design. |
| Done when | Meters field available; pre-fills from `design.estimatedMeters`; customer can edit. |

B-21 · Configurator step 4 — measurements form

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | B-17 |
| Description | Body measurements form with placeholder fields (all optional in MVP). |
| Done when | Page at `/custom-order/measurements` has chest, waist, hips, inseam, sleeveLength, notes. |

B-22 · Configurator step 5 — review + price breakdown

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-07, B-17, B-20 |
| Description | Order review screen with live itemized price breakdown from preview API. |
| Done when | Page at `/custom-order/review` calls preview API; shows receipt-style breakdown. |

B-23 · Custom checkout + place order

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-08, B-22, A-04 |
| Description | Final step — delivery address, COD confirm, submit custom order, show confirmation. |
| Done when | Checkout collects address; POSTs create order; shows confirmation screen. |

B-24 · Orders page — custom tab + live timeline

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-10, A-20 |
| Description | Custom orders tab on order history with real status timeline from order statusHistory. |
| Done when | Custom tab added; OrderTimeline wired to real statuses (map 8 backend statuses to UI). |

### Backend — Tailor portal (4 tasks)

B-25 · Tailor signup API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-01b |
| Description | Dedicated signup endpoint for tailors — creates pending account awaiting admin approval. |
| Done when | `POST /api/users/signup/tailor` sets role `tailor`, `approvalStatus: pending`; rejects duplicate email. |

B-26 · isApprovedTailor middleware

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-01b |
| Description | Backend guard ensuring only approved tailors can manage shop and designs. |
| Done when | Middleware checks role `tailor` + `approvalStatus: approved`; used on tailor routes. |

B-27 · Tailor shop API (own shop)

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | B-26, L-04 |
| Description | Let approved tailor create and update their single shop profile. |
| Done when | `GET/POST/PUT /api/tailor/shop` scoped to logged-in approved tailor; one shop per user. |

B-28 · Tailor designs CRUD API

| Assignee | Dev B |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | B-26, B-27, L-05 |
| Description | Let approved tailor manage their own design catalog and pricing fields. |
| Done when | `GET/POST/PUT/DELETE /api/tailor/designs` scoped to own shop; sets basePrice, tailoringFee, estimatedMeters. |

### Frontend — Tailor portal (4 tasks)

B-29 · Tailor registration page

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-01, B-25 |
| Description | Public page for tailors to register — explains account needs MOTD admin approval before going live. |
| Done when | Page at `/partners/tailor` submits signup; shows "awaiting approval" success; linked from Partner CTA. |

B-30 · Tailor dashboard layout + pending state

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-03, B-25 |
| Description | Tailor portal shell that shows different UI based on approval status (pending / rejected / approved). |
| Done when | Layout at `/tailor` shows waiting screen if pending, contact message if rejected, nav if approved. |

B-31 · Tailor shop profile form

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-27, B-30, P-05b |
| Description | Approved tailor edits their shop name, logo, description, location, and contact info. |
| Done when | Page at `/tailor/shop` saves to shop API; bilingual EN/AR fields. |

B-32 · Tailor designs management UI

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | B-28, B-30, P-05b |
| Description | Approved tailor CRUD UI for their design listings and pricing. |
| Done when | Page at `/tailor/designs` lists, creates, edits, deletes own designs. |

## DEV C tasks — Admin module (22 tasks)

### Backend — Admin CRUD (10 tasks)

C-01 · Admin middleware helper

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~1h |
| Blocked by | — |
| Description | Ensure reusable admin auth guard for all `/api/admin/*` routes. |
| Done when | `isAdmin` middleware exported and applied consistently in auth.js. |

C-02 · Admin ready-made CRUD API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | L-02, C-01 |
| Description | Admin API to create and manage ready-made items from size-return custom orders. |
| Done when | Full CRUD at `/api/admin/ready-made`; auto `countInStock: 1`; links source custom order. |

C-03 · Admin fabrics CRUD API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | L-03, C-01 |
| Description | Admin API to manage fabric catalog and fabric_store attribution. |
| Done when | Full CRUD at `/api/admin/fabrics`. |

C-04 · Admin tailor approval API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | L-01b, C-01 |
| Description | Admin API to review pending tailor signups and approve or reject them. |
| Done when | `GET /api/admin/tailors/pending`; PATCH approve/reject updates `approvalStatus` + optional note. |

C-05 · Admin tailor oversight API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | C-04 |
| Description | Admin read-only oversight of approved tailors with ability to deactivate a shop for moderation. |
| Done when | `GET /api/admin/tailors` lists accounts; PATCH deactivate toggles shop `isActive` (no content editing). |

C-06 · Admin retail orders API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | L-06, C-01 |
| Description | Admin API to list ready-made orders and update shipping status. |
| Done when | `GET /api/admin/orders/retail`; PATCH status (pending → confirmed → shipped → delivered). |

C-07 · Admin custom orders API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~4h |
| Blocked by | L-07, C-01 |
| Description | Admin API to manage custom order logistics pipeline and add status notes. |
| Done when | `GET /api/admin/orders/custom`; PATCH advances 8-step status + optional notes. |

C-08 · Admin dashboard stats API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | C-06, C-07 |
| Description | Aggregated stats for admin dashboard — order counts and revenue split. |
| Done when | `GET /api/admin/dashboard` returns retail vs custom counts and revenue split. |

C-09 · Admin platform settings API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~2h |
| Blocked by | L-01, C-01 |
| Description | Admin API to read and update platform-wide pricing defaults. |
| Done when | `GET/PUT /api/admin/settings` for delivery fee, VAT, tailoring defaults. |

C-10 · Admin fabric_store partners API

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Blocked by | C-01 |
| Description | Admin API to create/manage fabric store partner accounts (tailors self-register separately). |
| Done when | CRUD for `fabric_store` users at `/api/admin/users`; no manual tailor account creation. |

### Frontend — Admin UI (12 tasks)

C-11 · Admin layout + route guard

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | A-03 |
| Description | Admin panel shell with sidebar navigation; block non-admin users. |
| Done when | Layout at `/admin` with sidebar; redirects non-admin to login/home. |

C-12 · Admin dashboard page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | C-08, C-11 |
| Description | Admin home page showing key platform stats at a glance. |
| Done when | Dashboard at `/admin` shows stats cards from dashboard API. |

C-13 · Admin ready-made list page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | C-02, C-11 |
| Description | Admin table of all ready-made items with return context and availability. |
| Done when | List shows size, return reason, linked custom order, sold/available status. |

C-14 · Admin ready-made create/edit form

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | C-02, C-13 |
| Description | Admin form to list a new ready-made item when a custom order is returned for size. |
| Done when | Create/edit forms with source order, size, condition, price, images; no seller picker. |

C-15 · Admin fabrics list + form

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | C-03, C-11 |
| Description | Admin CRUD UI for fabric catalog entries. |
| Done when | List + create/edit pages at `/admin/fabrics`. |

C-16 · Admin pending tailors page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | C-04, C-11 |
| Description | Admin queue of tailor registration requests waiting for approval. |
| Done when | Page at `/admin/tailors/pending` with Approve / Reject actions. |

C-17 · Admin tailor oversight page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | C-05, C-11 |
| Description | Admin view of approved tailors and their shops; deactivate for moderation only. |
| Done when | Page lists approved tailors + shops; deactivate toggle; no shop/design edit forms. |

C-18 · Admin retail orders page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | C-06, C-11 |
| Description | Admin page to manage ready-made purchase orders and update delivery status. |
| Done when | List + status dropdown for retail order pipeline. |

C-19 · Admin custom orders page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~4h |
| Blocked by | C-07, C-11 |
| Description | Admin page to advance custom orders through logistics statuses. |
| Done when | List + status pipeline buttons (8 steps) + notes field. |

C-20 · Admin fabric_store partners page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | C-10, C-11 |
| Description | Admin UI to create and manage fabric store partner accounts. |
| Done when | Partners page manages `fabric_store` users only. |

C-21 · Admin platform settings page

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Blocked by | C-09, C-11 |
| Description | Admin form to edit platform defaults (delivery fee, VAT, tailoring fee). |
| Done when | Settings page saves to platform settings API. |

C-22 · Admin shared form components

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | — |
| Description | Reusable admin form building blocks to speed up all CRUD pages. |
| Done when | FormField, ImageUrlInput, StatusBadge components in `components/admin/`. |

## SHARED polish tasks (11 tasks) — assign after S2

P-01 · Fix Navbar broken anchor links

| Assignee | Any (suggest Dev A) |
| --- | --- |
| Type | Frontend |
| Est. | ~1h |
| Description | Fix navbar links that point to non-existent homepage section IDs. |
| Done when | `#custom-clothing`, `#stories` map to correct section IDs in Navbar. |

P-02 · Add i18n strings for all new pages

| Assignee | All devs (split by module) |
| --- | --- |
| Type | Frontend |
| Est. | ~4h total |
| Description | Add Arabic and English translations for all new pages and flows built in MVP. |
| Done when | `en.json` + `ar.json` cover auth, cart, checkout, configurator, tailor portal, admin. |

P-03 · AED + VAT formatting on all price UIs

| Assignee | Any |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Description | Apply consistent AED currency and VAT display across all modules. |
| Done when | All price displays use [`frontend/src/lib/format.ts`](frontend/src/lib/format.ts). |

P-04 · Loading + error UI components

| Assignee | Dev A (then reused) |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Description | Shared loading and error components for consistent UX across pages. |
| Done when | LoadingSpinner + ErrorMessage components used across A/B/C pages. |

P-05 · Protected route HOC

| Assignee | Dev A |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Description | Reusable wrapper that redirects unauthenticated users away from protected pages. |
| Done when | RequireAuth wraps checkout, orders, configurator, tailor portal routes. |

P-05b · RequireApprovedTailor guard

| Assignee | Dev B |
| --- | --- |
| Type | Frontend |
| Est. | ~2h |
| Description | Guard that blocks pending tailors from shop/design pages and shows waiting screen. |
| Done when | RequireApprovedTailor redirects pending tailors to dashboard waiting state. |

P-06 · Cloudinary upload endpoint

| Assignee | Dev C |
| --- | --- |
| Type | Backend |
| Est. | ~3h |
| Description | Backend endpoint for admin (and optionally tailor) image uploads via Cloudinary. |
| Done when | `POST /api/admin/upload` returns image URL; `CLOUDINARY_*` env vars documented. |

P-07 · Wire Cloudinary into admin forms

| Assignee | Dev C |
| --- | --- |
| Type | Frontend |
| Est. | ~3h |
| Blocked by | P-06 |
| Description | Replace manual image URL text inputs with upload buttons on admin forms. |
| Done when | Upload button on ready-made, fabric, and related admin forms. |

P-08 · MongoDB Atlas + production env

| Assignee | Lead or Dev C |
| --- | --- |
| Type | DevOps |
| Est. | ~3h |
| Description | Set up production MongoDB and document environment variables for deployment. |
| Done when | Atlas cluster live; production `.env` template; connection strings documented. |

P-09 · Deploy backend + frontend

| Assignee | Dev C or Lead |
| --- | --- |
| Type | DevOps |
| Est. | ~4h |
| Blocked by | P-08 |
| Description | Deploy API and Next.js app to chosen hosting with correct CORS and env config. |
| Done when | Frontend + backend live; `CORS_ORIGIN` updated; smoke test on production URLs. |

P-10 · E2E smoke tests

| Assignee | All (QA pass) |
| --- | --- |
| Type | Full-stack |
| Est. | ~4h |
| Blocked by | B-23, B-32, C-16 |
| Description | End-to-end manual or Playwright tests covering the three critical MVP paths. |
| Done when | (1) Custom order path works, (2) tailor signup → approve → shop/design live, (3) admin status update shows on customer timeline. |

## Suggested ClickUp list structure

Create 5 lists (or tags):

Lead — Foundation (L-01 → L-14, incl. L-01b)

Dev A — Auth + Ready-made (A-01 → A-20)

Dev B — Custom + Tailor portal (B-01 → B-32)

Dev C — Admin (C-01 → C-22)

Polish & Launch (P-01 → P-10, incl. P-05b)

### ClickUp custom fields to add

Assignee: Lead / Dev A / Dev B / Dev C

Type: Backend / Frontend / Full-stack / Docs / DevOps

Module: Foundation / Ready-made / Custom / Tailor portal / Admin / Shared

Blocked by: e.g. "L-06", "A-01"

Estimate: Match Est. column in each task (~1h–4h)

### ClickUp copy example

Task name: B-25 · Tailor signup API

Description (paste): Dedicated signup endpoint for tailors — creates pending account awaiting admin approval.

Acceptance criteria (paste in checklist or subtask):

POST /api/users/signup/tailor sets role tailor, approvalStatus: pending

Rejects duplicate email

## Critical path

[Flowchart diagram — see digital plan for visual]

Start order:

Lead: L-01 → L-08 (models) — hard gate for all devs

Day 1 parallel: Dev A → A-01 · Dev B → A-03 + B-01 · Dev C → C-01

All devs: backend APIs in parallel (no need to wait for full auth UI)

After A-01: frontend API integration starts everywhere

After A-03: checkout, admin, tailor portal protected routes

Lead: seed L-09–L-14 (can overlap with step 3–4)

Polish + deploy last

## Out of scope (do not add to ClickUp yet)

Online payments (Moyasar) — post-MVP

Seller portal / seller role (ready-made is admin-only)

Delivery self-service portal

Phone OTP auth

Newsletter backend

Wishlist / search functionality

## Task count summary

| Owner | Tasks | Notes |
| --- | --- | --- |
| Lead | 15 | Sequential — unblocks team |
| Dev A | 24 | Ready-made + shared auth UI + catalog pages |
| Dev B | 25 | Custom flow + auth context + tailor backend |
| Dev C | 25 | Admin + signup + tailor frontend |
| Shared polish | 11 | Final week — split ~3–4 each |
| Total | 100 ClickUp tasks | Devs: 74 tasks ÷ 3 ≈ 25 each |

Custom tailoring is the priority track. Ready-made (Dev A) can slip without blocking Dev B/C. S1 is not a full sprint for one person — only A-01 + A-03 (~6h total) gate protected frontend; everything else runs in parallel from day one after Lead models.